## Dashboard
nVision CONSULTING GROUP
Managed Service Practice Development — Execution Tracker
Dashboard rollup • update status on the Action Tracker tab
PROGRESS BY STATUS | Count | Share
Not Started | 49 | 100%
In Progress | 0 | 0%
Complete | 0 | 0%
Blocked | 0 | 0%
N/A | 0 | 0%
Total actions | 49 | 100%
% COMPLETE | 0%
Complete ÷ (Total − N/A)
PROGRESS BY PHASE | Total | Done | Blocked | % Complete
Discover | 6 | 0 | 0 | 0%
Develop | 33 | 0 | 0 | 0%
Deliver | 10 | 0 | 0 | 0%
HOW TO USE
1. Go to the Action Tracker tab. Each of the 49 actions has a fixed ID (e.g., DV12) matching the playbook.
2. Fill only the shaded input columns: Priority, Status, Target Date, Completed Date, Notes.
3. Set Status from the dropdown — the Dashboard and cell colors update automatically.
4. Each action links to its template in the online playbook (Playbook template column).
STATUS KEY
Not Started | Not yet begun (default).
In Progress | Work underway.
Complete | Finished and validated.
Blocked | Stalled on a dependency or decision.
N/A | Not applicable to this business/model.

## Action Tracker
nVision ¦ Managed Service Practice Development Action Plan — Execution Tracker
Editable columns are shaded: Priority • Status • Target Date • Completed Date • Notes. Set Status via the dropdown.
ID | Phase | Workstream | Recommended Action | Owner | Priority | Status | Target Date | Completed Date | Notes | Playbook template
D1 | Discover | Qualification and Readiness | Understand the managed services market opportunity and how it applies to your business. | Exec Sponsor |  | Not Started |  |  |  | Qualification and Readiness Assessment
D2 | Discover | Qualification and Readiness | Given your existing capabilities, evaluate and determine the managed service business model that you will pursue. | Exec Sponsor |  | Not Started |  |  |  | Qualification and Readiness Assessment
D3 | Discover | Qualification and Readiness | Utilizing the Qualification and Readiness Assessment and other available information, determine your business readiness and priority for this initiative. | Exec Sponsor and Extreme PAM |  | Not Started |  |  |  | Qualification and Readiness Assessment
D4 | Discover | Securing Executive Commitment | Affirm your executive commitment and assign an executive sponsor with the full authority to develop Extreme managed service capabilities and/or new Extreme managed service offerings. | Exec Team |  | Not Started |  |  |  | Executive Commitment and Team Roster
D5 | Discover | Securing Executive Commitment | Secure your extended leadership team support and commitment. | Exec Sponsor |  | Not Started |  |  |  | Executive Commitment and Team Roster
D6 | Discover | Securing Executive Commitment | Establish the working team that will develop and execute on the managed services practice development action plan and the recommendations in this playbook. | Leadership Team |  | Not Started |  |  |  | Executive Commitment and Team Roster
DV1 | Develop | Business and Financial Planning | Formulate your managed services vision and mission statements. These can be captured in Table 4 of the playbook. | Exec Team |  | Not Started |  |  |  | Vision, Mission, and Business Priority
DV2 | Develop | Business and Financial Planning | Utilize Table 3 to determine the Extreme managed services business model that will be most appropriate for your business. | Managed Services Leader |  | Not Started |  |  |  | Managed Services Business Model Selector
DV3 | Develop | Business and Financial Planning | Analyze your installed base of customers to understand your managed services opportunity and the likely service requirements of your customers. | Marketing Leadership |  | Not Started |  |  |  | Installed Base and Service Evaluation Matrix
DV4 | Develop | Business and Financial Planning | Perform a SWOT analysis to identify opportunities to establish competitive differentiation. | Marketing Leadership or Managed Services Leader |  | Not Started |  |  |  | SWOT and Competitive Differentiation
DV5 | Develop | Business and Financial Planning | Utilizing Table 5, establish your UVPs for target customers, business partners (i.e., Extreme partners), and internal stakeholders. | Marketing Leadership |  | Not Started |  |  |  | Unique Value Proposition
DV6 | Develop | Business and Financial Planning | Model your anticipated financial performance for managed services, and define your financial objectives. Utilize Table 6 to capture these objectives. | Executive Team |  | Not Started |  |  |  | Financial Objectives and Investment Model
DV7 | Develop | Business and Financial Planning | Develop your Managed Services Business Plan that outlines your financial and development objectives, tasks, activities, and timelines. | Managed Services Manager |  | Not Started |  |  |  | Managed Services Business Plan Outline
DV8 | Develop | Business and Financial Planning | Establish practice-level, leadership, and individual MBOs / OKRs to drive performance and accountability for execution. | Leadership Team |  | Not Started |  |  |  | MBO / OKR Scorecard
DV9 | Develop | Extreme Agile Service Creation | Drawing upon your market and installed base research, segment customers to identify differentiated managed service requirements. | Managed Services Leader or Product Manager |  | Not Started |  |  |  | Installed Base and Service Evaluation Matrix
DV10 | Develop | Extreme Agile Service Creation | Based on your analysis, utilize Table 7 to identify 3 candidate managed services, outline the segment requirements, and quantify strategic value and priority. | Managed Services Leader or Product Manager |  | Not Started |  |  |  | Installed Base and Service Evaluation Matrix
DV11 | Develop | Extreme Agile Service Creation | Facilitate a Managed Service Discovery Workshop to vet the potential managed services, determine which to advance, and begin to identify the managed service framework. | Managed Services Leader or Product Manager |  | Not Started |  |  |  | Market Segmentation and New Service Idea
DV12 | Develop | Extreme Agile Service Creation | Utilize Table 8 to develop a New Managed Service Idea Presentation to capture high-level service details to vet with prospective buyers and take forward for a concept commit. | Managed Services Leader or Product Manager |  | Not Started |  |  |  | Market Segmentation and New Service Idea
DV13 | Develop | Extreme Agile Service Creation | Engage target buyers, through digital marketing, surveys, or focus groups, to validate the high-level managed service concept. | Managed Services Leader or Product Manager |  | Not Started |  |  |  | Market Segmentation and New Service Idea
DV14 | Develop | Extreme Agile Service Creation | Confirm internal concept commit to ensure the resource allocation and investment required to develop your new managed service. | Managed Services Leader or Product Manager |  | Not Started |  |  |  | Managed Service Definition (MSD) and Creation Workshop
DV15 | Develop | Extreme Agile Service Creation | Using the agenda in Exhibit 1 and the Managed Service Development Template in Table 9, facilitate a Managed Service Creation Workshop to develop your new managed service elements in detail. | Managed Services Leader or Product Manager |  | Not Started |  |  |  | Managed Service Definition (MSD) and Creation Workshop
DV16 | Develop | Extreme Agile Service Creation | Evaluate opportunities to package or bundle your new managed service with other offers. Define the specific requirements of doing so. | Managed Services Leader or Product Manager |  | Not Started |  |  |  | Packaging, Bundling, and Pricing
DV17 | Develop | Extreme Agile Service Creation | Based on the managed service requirements defined and the unique value offered, determine pricing for your new managed service. | Managed Services Leader or Product Manager |  | Not Started |  |  |  | Packaging, Bundling, and Pricing
DV18 | Develop | Extreme Agile Service Creation | Based on updated managed service constructs, investment requirements, and pricing, update, finalize, and obtain agreement of the business case. | Managed Services Leader or Product Manager |  | Not Started |  |  |  | Packaging, Bundling, and Pricing
DV19 | Develop | Extreme Agile Service Creation | Where possible, validate the offering one final time with your prospective buyers through digital marketing. | Managed Services Leader or Product Manager |  | Not Started |  |  |  | Market Segmentation and New Service Idea
DV20 | Develop | Extreme Agile Service Creation | Develop an MSD outlining the features of the new managed service. | Managed Services Leader or Product Manager |  | Not Started |  |  |  | Managed Service Definition (MSD) and Creation Workshop
DV21 | Develop | Extreme Managed Service Product Development | Define your requirements for both NOC and service desk. | Managed Services Leader or Product Manager |  | Not Started |  |  |  | NOC and Service Desk Strategy
DV22 | Develop | Extreme Managed Service Product Development | Evaluate your NOC and service desk requirements and determine the most appropriate strategy to deliver NOC and service desk capabilities. | Delivery Leader or Business Operations Leader |  | Not Started |  |  |  | NOC and Service Desk Strategy
DV23 | Develop | Extreme Managed Service Product Development | Based on your new managed service delivery requirements, define the platform requirements for provisioning, managing, maintaining, and billing. | Managed Services Leader or Product Manager |  | Not Started |  |  |  | Platform and Tools Requirements
DV24 | Develop | Extreme Managed Service Product Development | Based on your platform requirements, identify, procure, and configure the platforms required for provisioning, managing, maintaining, and billing for the new managed services. | Delivery Leader or Business Operations Leader |  | Not Started |  |  |  | Platform and Tools Requirements
DV25 | Develop | Extreme Managed Service Product Development | Create and configure the Extreme Platform ONE dashboard. | Delivery Leader |  | Not Started |  |  |  | Platform and Tools Requirements
DV26 | Develop | Extreme Managed Service Product Development | Establish integration between your new platforms and your existing OSS/BSS/PSA platforms to ensure seamless hand-offs, delivery, and visibility. | Delivery Leader |  | Not Started |  |  |  | Platform and Tools Requirements
DV27 | Develop | Extreme Managed Service Product Development | Define your new managed services ordering processes and ensure the business rules are established in your OSS/BSS/PSA platforms. | Business Operations Leader |  | Not Started |  |  |  | Rules of Engagement and Handoffs (RACI)
DV28 | Develop | Extreme Managed Service Product Development | Establish a lab environment that can validate your services before launch and be utilized for replicating customer problems and troubleshooting. | Delivery Leader |  | Not Started |  |  |  | Platform and Tools Requirements
DV29 | Develop | Extreme Managed Service Product Development | Define your customer onboarding process and methodologies. | Delivery Leader |  | Not Started |  |  |  | Customer Onboarding Plan
DV30 | Develop | Extreme Managed Service Product Development | Define your rules of engagement to transition from onboarding to live. | Delivery Leader |  | Not Started |  |  |  | Customer Onboarding Plan
DV31 | Develop | Extreme Managed Service Product Development | Define and execute your new managed service marketing plan, including required collateral. | Marketing Leader |  | Not Started |  |  |  | Marketing Assets and Demand Generation Plan
DV32 | Develop | Extreme Managed Service Product Development | Determine your sales routes to market for each target customer segment and/or buyer persona. | Sales Leader |  | Not Started |  |  |  | Go-to-Market Plan and Routes to Market
DV33 | Develop | Extreme Managed Service Product Development | Utilize Table 13 to develop and execute a sales readiness plan for each route to market. | Sales Leader |  | Not Started |  |  |  | Sales Readiness and Enablement Plan
DL1 | Deliver | GTM Planning and Managed Service Launch | Develop your GTM plan to take your new managed services to market. | Managed Services Leader |  | Not Started |  |  |  | Go-to-Market Plan and Routes to Market
DL2 | Deliver | GTM Planning and Managed Service Launch | Assess sales readiness relative to the skills and capacity required to take your new managed services to market. | Sales Leader |  | Not Started |  |  |  | Sales Readiness and Enablement Plan
DL3 | Deliver | GTM Planning and Managed Service Launch | Develop and execute a sales enablement plan to ensure your sales organization understands and can position the value, capabilities, and features of your new managed service, the sales motions, customer onboarding, and service delivery. | Sales Leader |  | Not Started |  |  |  | Sales Readiness and Enablement Plan
DL4 | Deliver | GTM Planning and Managed Service Launch | Establish sales KPIs / OKRs that are aligned to your GTM plan and your overarching managed service business plan. | Sales Leader |  | Not Started |  |  |  | KPI Scorecard: Customer Outcomes and Business Performance
DL5 | Deliver | GTM Planning and Managed Service Launch | Evaluate sales compensation to ensure it aligns to your managed service business plan, will drive accountability for sales execution, and will reward sales for superior performance. | Sales Leader |  | Not Started |  |  |  | Sales Compensation and Incentive Planner
DL6 | Deliver | GTM Planning and Managed Service Launch | Utilizing Table 14, establish a structured pilot that will validate your new managed services capabilities. | Managed Services Leader |  | Not Started |  |  |  | Managed Service Piloting Checklist
DL7 | Deliver | GTM Planning and Managed Service Launch | Execute your structured pilot and address gaps identified. | Managed Services Leader |  | Not Started |  |  |  | Managed Service Piloting Checklist
DL8 | Deliver | GTM Planning and Managed Service Launch | Based on the success of the pilot, develop customer use cases and testimonials that can be used in your launch. | Managed Services Leader |  | Not Started |  |  |  | Customer Success Plan and QBR
DL9 | Deliver | GTM Planning and Managed Service Launch | Identify initial Phase 1 target customers in prep for launch. | Sales Leader |  | Not Started |  |  |  | Target Segments and Accounts
DL10 | Deliver | GTM Planning and Managed Service Launch | Launch your new Extreme managed services offering(s). | Managed Services Leader |  | Not Started |  |  |  | Go-to-Market Plan and Routes to Market